## Slide 1
EarthCARE CalVal Team
Roadmap
Rob Koopman, Rob.Koopman@esa.int
1st ESA EarthCARE Cal/Val Workshop, 13-15 June 2018, Bonn

## Slide 2: 11) Timeline/Next Steps
Workshop report Q3 2018
Notification of acceptance/letter of support Q3 2018
Validation plan (1.0) Q4 2018
Funding confirmation (may involve proposals to national or international calls) 2018 &’19
Intention to host a Validation Methods workshop (TBC) Q3 2019
(ESA and PI) to describe which of the activities proposed in the AO are confirmed 2019 &’20
ESA-JAXA validation workshop October 2020
Validation Plan (2.0) Q4 2020
Validation Rehearsal Q1 2021
Validation Rehearsal Review / Validation Readiness Q2 2021
Launch June 2021
Preliminary Validation Results Review Launch + 6M
Long-term Validation Phase Launch+6 months until End of Mission

## Slide 3: Near-term documents
Item | Authors
Validation Workshop Report | E-MAG, ESA
Validation Plan (1.0) | ESA, ECVT, E-MAG

## Slide 4: Other take-away points (in random order)
(Apart from the session conclusions)
Need for process for input from ECVT to Algorithm Developers (to be mapped on the Cal/Val portal), with feedback loop
Consider webex information sessions on tools, format conversion
Consider focused subgroups for ECVT (e.g. per EarthCARE parameter family)
Support from EVDC for data upload: organise per network, for large networks
Make explicit when a proposal depends on data from an external provider (e.g. non-ACTRIS stations from AERONET, SKYNET etc)
Promote use of data from past campaigns (many NASA campaigns and EPATAN etc.)

## Slide 5
Thank you for your contributions to a productive workshop